## summary
FEATURES
Feature Status | Count of STATUS
Close | 5
In Progress | 0
Not Started | 0
TESTCASE
Tesrcase Status | Count of STATUS
Close | 4
In Progress | 0
Not Started | 0

## features_extraction
FEATURE ID | FEATURE | DESCRIPTION | PRIORITY (P1, P2, P3) | IMPLEMENTATION DETAILS | TEST NAME | COMMENTS | Status | Effort | Remaining Effort
LOCK_01 | Password Entry FSM | Sequentially collects 4 digits | P1 | FSM written in Verilog | test_correct_password |  | Completed | 4 hrs | 0 hrs
LOCK_02 | Password Matching | Compares entered digits with hardcoded pwd | P1 | Comparison logic in FSM | test_correct_password |  | Completed | 2 hrs | 0 hrs
LOCK_03 | Error Detection | Detects incorrect password | P1 | Conditional mismatch logic | test_wrong_password |  | Completed | 2 hrs | 0 hrs
LOCK_04 | Self-checking Testbench | Checks both correct and wrong inputs | P2 | Automated testbench with pass/fail printing | door_lock_tb |  | Completed | 3 hrs | 0 hrs
LOCK_05 | Reset Functionality | Brings FSM back to IDLE | P2 | Reset in always block | test_reset |  | Completed | 1 hr | 0 hrs

## testcases
TEST NAME | DESCRIPTION | TESTCASE STEPS | PRIORITY (P1, P2, P3) | COMMENTS | IMPLEMENTATION STATUS
test_correct_password | Test correct 4-digit password | Enter 4-1-3-2 → verify unlock signal = 1 | P1 |  | Completed
test_wrong_password | Test wrong 4-digit password | Enter 1-2-3-4 → verify error signal = 1 | P1 |  | Completed
door_lock_tb | Full testbench validation | Run both test cases using self-checking TB with $display outputs | P2 |  | Completed
test_reset | Reset test | After any test, apply reset → system should return to IDLE state | P2 |  | Completed